## Slide 1
State Employee's Credit Union
Project Bid by ACDC

## Slide 2
Team and Responsibilities
Amber Garcia – Project Manager
Daniela Morales – Scheduler
Cody Lovelace – Estimator

## Slide 3
Project Information
Key Points
  State Employee Credit Union Information
  Visual Components
  Contractual Constraints

## Slide 4
Project Information
ACDC's Project Team
Contractor: ACDC
Client: State Employee Credit Union
Design Team: O'Brien/Atkins Associates, P.A.
Structural Engineer: GKC Associates
Civil Engineer: McKim & Creed Engineers
Notes: https://www.hmgeneralcontractors.com/blog/houston-design-construction-team

## Slide 5
Project Information
Location
Providence Road Office
Corner of Providence Road and Allison Woods Drive
Charlotte, North Carolina

## Slide 6
Brief Overview of Site Plan
New Belle Rea Road Addition
Erosion Controls
EROSION
CONTROL
EROSION
CONTROL

## Slide 7
Scope of Work

## Slide 8
Scope of Work
Primary Materials
SECU Information
10,504 Sq. Ft.
Single-Story
Drive-Thru Access
Parking lot
Project Description
State Employee Credit Union is a new commercial construction building which will offer financial services and job opportunities for its hometown. Project will begin January 3rd and be completed November 20th.
Cast-in-Place Concrete​
Light Guage Steel Framing​
Type A & Type B Brick​
Pre-manufactured Trusses​

## Slide 9
First Floor Plan

## Slide 10
Elevations

## Slide 11
Scope of Work
Goals
To successfully build SECU Project on budget, on time, and efficiently
Project Deadlines
Belle Rea Rode is to be constructed withing the first 120 consecutive days
Contract & Contractual Constraints
Progress payments shall be submitted once a month for payments to be made on the 15th of each month for work completed
Belle Rea Road Addition – 120 Days
Project Completion – 300 Days

## Slide 12: Means and Methods

## Slide 13: Site Layout
GATE 1
GATE 2
CRANE
TRAILER
MATERIAL
LAYDOWN
LAYDOWN
PARKING LOT
ENTRANCE
Key:
Dumpster
Port-a-Johns
Flow of Traffic
Fence
Notes: LEGEND LEFT

## Slide 14
WBS

## Slide 15: SECU 2. Site Preparation & 3. Sitework
Rough Grading of Site
Prepare Building Pad
Belle Rea Road
Site Clearing
Volvo EC330BLC 1.5 Cy Bucket Excavator
Dejana Titan 8cy Dump Truck
Notes: Site Clearing
Rough Grading of Site
Belle Rea Road

## Slide 16: SECU 4. Foundation
N
W

## Slide 17: SECU 4. Foundation
N
W

## Slide 18: SECU 4. Foundation
N
W

## Slide 19: SECU 5. Structure
12 Ton Terex BT2463
N
W
Notes: Beams, Steel Frame, Pre-Fab Vault, Pre-Fab Trusses

## Slide 20: SECU 5. Structure
JLG RT3369 Scissor Lift
Notes: SCAFFOLDING AND LULL

## Slide 21: SECU 5. Structure

## Slide 22: SECU 6. Openings, SECU 7. Services, & SECU 8. Finishes
Notes: MEP SCISSORLIFT INSIDE

## Slide 23: Project Estimate

## Slide 24: Project Estimate Overview
Resources Used:
Construction Team's Quantity Takeoff
RS Means (Cost factors for Material, Labor, Equipment)

## Slide 25: Cost Breakdown By Division
DIVISION | Direct Cost
Division 03 Concrete | $ 307,084.95
Division 04 Masonry | $ 59,947.63
Division 05 Metals | $189,309.56
Division 08 Openings | $ 78,302.00
Division 09 & 10 Finishes & Specialties | $ 295,305.78
Division 22 Plumbing | $ 78,042.75
Division 23 HVAC | $ 19,114.42
Division 26 Electrical | $ 38,077.78
Division 31 Earthwork | $ 144,652.65
Division 32 Exterior Improvements | $173,754.63
Division 33 Utilities | $ 109,025.32
TOTAL DIRECT COST | $ 1,492,618.47

## Slide 26: Material, Labor, Equipment, & Allowances Total Costs
Division | Total Material Cost | Total Labor Cost | Total Equipment Cost | Total Allowances | Direct Cost
Division 03 Concrete | $ 93,901.28 | $ 204,342.51 | $ 8,841.15 | N/A | 
Division 04 Masonry | $ 15, 678.25 | $ 44,269.37 | N/A | N/A | 
Division 05 Metals | $ 139,908.94 | $ 44,542.36 | $ 4,858.26 | N/A | 
Division 08 Openings | $ 56,752.00 | $ 21,550.00 | N/A | N/A | 
Division 09 & 10 Finishes and Specialties | $81,980.39 | $ 32,685.32 | $ 205.08 | $ 180,435 | 
Division 22 Plumbing | $ 40,342.45 | $ 37,700.30 | N/A | N/A | 
Division 23 HVAC | $ 10,083.62 | $ 9,030.80 | N/A | N/A | 
Division 26 Electrical | $ 21,927.00 | $ 16,150.78 | N/A | N/A | 
Division 31 Earthwork | $ 40,915.02 | $ 32,100.56 | $ 71,638.08 | N/A | 
Division 32 Exterior Improvements | $ 100,677.25 | $ 64,828.88 | $ 8,248.50 | N/A | 
Division 33 Utilities | $ 64,909.60 | $ 34,844.31 | $ 9,271.41 | N/A | 
Total | $ 667,075.80 | $ 542,045.20 | $ 103,062.47 | $ 180,435 | $ 1,492,618.47

## Slide 27: Indirect & Overhead
Indirect Project Cost & Overhead:
$ 394,775.26
Field Personal
Office Overhead
Mobilization/Demobilization
Mobile Office Trailor, Port-a-Johns, Security fencing
Permits, Insurance, Bonding

## Slide 28: Contingency
No Contingency Markup
All Architectural & Engineering Plans are 100% for Construction Documents
Addendums provided

## Slide 29: Project Profit
Project Expected Profit
$ 335,839.16
Profit amount based on roughly 15% of Project Price

## Slide 30: Project Price
When adding all Project Costs (Direct, Indirect, and Overhead) and Project Profit the Estimated Price for the SECU Project is
$ 2,223,232.89

## Slide 31: Project Cost, Profit, & Price
The Total Cost of labor, materials, equipment, Indirect & Overhead (both project and office)
The Project Profit is accounts for 15% of the Projects Price
The Projects Price is the grant total for Direct costs, Indirect Costs, Overhead & Profit
Project Cost | Project Profit | Project Price
$ 1,887,393.73 | $ 335,839.16 | $ 2,223,232.89

## Slide 32: Project Schedule

## Slide 33: Project Schedule Overview
Project Milestones:
Milestone 1: Notice to Proceed- Jan. 3, 2012
Milestone 2: Belle Rea Road Completion- Feb. 24, 2012
Milestone 3: Project Complete- Nov. 20, 2012
Owner Constraints:
300 Total Workdays
Complete Belle Rea Road First 120 Workdays
Weather Delays Past 5-Years Data for Charlotte, NC
46 days

## Slide 34: Critical Path Schedule
January –March
Mobilize: Jan. 03, 2012
Earthwork
Underground Utilities
April – June
Building Foundation
Building In the Dry
July – September
Exterior Wall Masonry
MEP Rough In
Spray-Foam Insulation
Hang Drywall
MEP Finish
October – November
Storefront Windows
Owner-Furnished Equipment
Install Flooring
Punchlist
Clean Up / Demobilize
Project Complete: Nov. 20, 2012
Mobilize Crane

## Slide 37: Analysis

## Slide 38
Payment Terms & Requirements
Progress payments once a month
10% Retainage
15% Profit
Cost Loading Schedule Calculations |  |  |  |  |  |  |  |  |  |  | 
 | January | February | March | April | May | June | July | August | September | October | November
Direct Cost | $ 210,203.95 | $ 130,431.70 | $ 59,012.66 | $ 136,777.96 | $ 145,207.34 | $ 112,245.04 | $ 80,079.52 | $ 129,596.76 | $ 129,730.75 | $ 224,563.28 | $ 975.00
Indirect Cost | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98 | $ 35,729.98
Total Cost | $ 245,933.93 | $ 166,161.68 | $ 94,742.64 | $ 172,507.94 | $ 180,937.32 | $ 147,975.02 | $ 115,809.50 | $ 165,326.74 | $ 165,460.73 | $ 260,293.26 | $ 36,704.98
Cumulative Cost | $ 245,933.93 | $ 412,095.62 | $ 506,838.26 | $ 679,346.20 | $ 860,283.53 | $ 1,008,258.55 | $ 1,124,068.06 | $ 1,289,394.80 | $ 1,454,855.53 | $ 1,715,148.80 | $ 1,751,853.78
Cost Loading Schedule

## Slide 40
 | Jan | Feb | March | Apr | May | June | July | Aug | Sept | Oct | Nov
Total Monthly Costs | $ 125,227.21 | $ 153,129.37 | $ 176,598.53 | $ 210,733.51 | $ 281,150.53 | $ 136,237.35 | $ 111,460.81 | $ 134,798.74 | $ 169,082.61 | $ 173,789.43 | $ 39,033.67
Total Monthly Profit (15%) | $ 18,784.08 | $ 22,969.41 | $ 26,489.78 | $ 31,610.03 | $ 42,172.58 | $ 20,435.60 | $ 16,719.12 | $ 20,219.81 | $ 25,362.39 | $ 26,068.41 | $ 5,855.05
Total Monthly Invoice | $ 144,011.29 | $ 176,098.77 | $ 203,088.31 | $ 242,343.53 | $ 323,323.11 | $ 156,672.95 | $ 128,179.93 | $ 155,018.55 | $ 194,445.00 | $ 199,857.84 | $ 44,888.72
Total Monthly Retainage (10%) | $ 14,401.13 | $ 17,609.88 | $ 20,308.83 | $ 24,234.35 | $ 32,332.31 | $ 15,667.30 | $ 12,817.99 | $ 15,501.85 | $ 19,444.50 | $ 19,985.78 | $ 4,488.87
Total Monthly Received | $ 129,610.16 | $ 158,488.90 | $ 182,779.48 | $ 218,109.18 | $ 290,990.80 | $ 141,005.66 | $ 115,361.94 | $ 139,516.69 | $ 175,000.50 | $ 179,872.06 | $ 40,399.85
Cumulative Received | $ 129,610.16 | $ 288,099.06 | $ 470,878.53 | $ 688,987.71 | $ 979,978.51 | $ 1,120,984.17 | $ 1,236,346.10 | $ 1,375,862.80 | $ 1,550,863.30 | $ 1,730,735.36 | $ 1,771,135.20
Payment Received Graph

## Slide 42
Highlight of Total Cash Deficit
Maximum Deficit
Expense = $946,839.14
Income = $688,987.72
Max. Deficit = $257,851.42

## Slide 43: Conclusion
SECU Project Price: $2,223,232.89
SECU Project Duration: 223 Days (Start: Jan. 3 – Finish: Nov. 20)
Expected Profit: $ 335,839.16